## Decisions
Category | Significance | Status | Title | Description | Decision | Alice Agreed | Bob Agreed | Carol Agreed | Notes | Meeting Date | Meeting Reference
Go-to-Market | 2 | Agreed | Target 5,000 active users before funding | Discussion about community size target before the next funding round. Initial proposal of 10,000 was considered too aggressive. | Target 5,000 active users before next funding round | Yes | Yes | Yes | Bob initially proposed 10,000, Alice suggested 5,000 as more achievable, Carol supported 5,000 noting 'quality over quantity', Bob agreed to support 5,000, Alice confirmed 'I love that target. 5,000 active users it is.' |  | sample-transcript-1.txt
Go-to-Market | 2 | Unresolved | Growth spending vs sustainability approach | Discussion about whether to spend aggressively on growth or focus on sustainability. Bob raised concerns about cloud costs, Carol emphasized market window timing. | No decision reached | No | No | No | Alice: 'Let's park this for now. We need more data on unit economics before deciding.' Bob agreed to revisit next week with cost projections. Carol expressed frustration: 'we can't keep delaying this decision.' |  | sample-transcript-1.txt
Product Tiers | 2 | Agreed | Anonymous tier for frictionless adoption | Discussion about authentication requirements - whether to require login for all features or allow anonymous access. Trade-offs between analytics and user friction were considered. | Offer anonymous tier for basic features; users can upgrade to accounts when they want to save their work | Yes | Yes | Yes | Carol emphasized 'reducing friction is critical for adoption', Alice agreed and proposed anonymous tier, Bob supported noting 'We can still track anonymous sessions with cookies for basic analytics', Carol confirmed 'we're agreed - anonymous tier for frictionless adoption' |  | sample-transcript-1.txt
Technical Architecture | 2 | Needs Clarification | Proxy cache as baseline caching strategy | Discussion of client-side caching strategy for mobile team. Two options considered: proxy cache (stores exact server responses, simple implementation) vs condensed cache (transforms/personalizes data, uses less storage). Proxy cache chosen for v1 due to simpler implementation (1 week vs 3-4 weeks) and faster performance for repeated requests. | Use proxy cache approach for v1, with plan to optimize later based on real usage data | Yes | Partial | Yes | Bob explicitly flagged open questions: 'I'm still confused about some edge cases. Like, what happens when the server schema changes? Do we invalidate the entire cache? And what about when a user is offline and we have stale data?' He agreed to document these in a technical spec by Friday. While aligned on direction, critical edge cases remain unresolved. |  | sample-transcript-2.txt
Technical Architecture | 2 | Agreed | URL-based API versioning with deprecation policy | Discussion of API versioning strategy between URL-based (/v1/users) and header-based approaches. URL-based chosen for better discoverability in logs and documentation. Policy includes supporting current version plus one previous version, with six month deprecation window for partners. | URL-based versioning using /v1/, /v2/ format. Support current plus one previous version. Six month deprecation notice before sunsetting old versions. | Yes | Yes | Yes | Bob: 'URL-based versioning is way more discoverable. When partners are debugging, they can see the version right in their logs.' Carol: 'The design team prefers URL-based too.' All explicitly agreed to six month deprecation timeline. |  | sample-transcript-2.txt
Technical Architecture | 3 | Agreed | Standardized API error response format | Agreement to standardize error responses across all API endpoints. Currently different endpoints return errors differently causing confusion for partners. | Standard JSON error format with fields: code (machine readable), message (human readable), details (optional additional context), and request_id (correlation ID for debugging). Standard REST HTTP status codes: 400, 401, 403, 404, 429, 500. | Yes | Yes | Yes | Bob proposed the structure. Carol added request_id requirement: 'When partners report issues, it's super helpful to have a correlation ID.' Bob agreed to include in Friday spec. |  | sample-transcript-2.txt
Terminology | 3 | Agreed | Rules vs recommendations documentation terminology | Standardizing documentation language to distinguish between hard requirements and guidance. Currently inconsistent use of 'you must do X' vs 'we recommend doing X'. | 'Rules' for testable/enforceable requirements (build will fail if violated). 'Recommendations' for matters of taste and judgment requiring human discretion. | Yes | Yes | Yes | Bob confirmed understanding with example: 'functions must have type annotations would be a rule, but prefer descriptive variable names would be a recommendation?' Carol: 'I like that distinction. It's clear and actionable.' Alice will update style guide. |  | sample-transcript-2.txt

## Summary
Decisions Summary
Input File | Decisions | Participants | Deciders
Total Decisions | 7

## Produced By
Groundtruth
Tool | groundtruth
Repository | https://github.com/rsnodgrass/groundtruth
Generated | 2025-12-17 20:15:48
Author | ryan
Quick Reference: Significance & Agreement Standards
Level | Label | Agreement Standard
1 | Critical | ALL must explicitly agree; any ambiguity = No
2 | Extremely Important | ALL must explicitly agree; any ambiguity = No
3 | Important | Any hint of misalignment = Partial or No
4 | Moderate | Clear alignment; slight ambiguity OK
5 | Same Page | General alignment sufficient
Agreement: Yes (explicit), Partial (hedged), No (silent/parked/disagreed)